## 4.1
PROJECT DETAILS
(Rs. in Crore)
Name of the Project: | Construction of carriage way from 2-Lane to 4-Lane of Ghatiapada-Sinapali road from 0/000 km to 52/000 km Including one major birdge in the district of Nuapada ( Pacakage 4.1) under Biju expressway through EPC Mode.
Scheme of the Work | State plan
Project Brief: | Construction of carriage way from 2-Lane to 4-Lane for a length of 52.65 Km | [5 empty] | * Project Brief :- 1. In Road Projects, mention the total length of the project with length of Flexible & Rigid Pavement. No. of Major/ Minor Bridges with span arrangement if any. 2. In Building Projects, mention the Construction Area. 3. In Bridge Projects, mention the Span Arrangement.
Division: | Khariar (R&B) Division | Assembly Consituency: | Khariar | District Name: | Nuapada
Estimated Cost (A/A Cost): (Revised A/A Cost, If any) | 14289.77 Lakhs |  |  | Agreement Value including GST: | 12208.31 Lakhs
Name of the Agency/Contractor with Contact No.: | Sri Durga Condev (P) Ltd. Mob No.-9937431041
Date of Commencement | 01.10.2021 | Stipulated Date of Completion: |  | 31.03.2023
Project In charge (Name of EE & Number): | Er. K K Panda (9437136900)
PRE-CONSTRUCTION ACTIVITIES - EXTERNAL | [5 empty] | Updated On (Date):
Category I | Issues with Revenue and Disaster Management Department
1. Land Acquisition Issues: | 11.577 acre (49tenants): LA under process SIA study completed Public hearing to be done from 22.12.2021. NOCs have been received from tenants No issues for construction work
2. Encroachment Issues: | --
3.Issues related to Government Land: | --
4. Any Other issues:
Category II | Issues with Forest and Environment Department
1. Forest Clearance Issues: | --
2. Issues related to Tree Felling permission: | --
3. Wild Life Management Plan | --
4. Any other issues: | --
Category III | Issues with Energy Department
1. Distribution Companies including shifting of poles and electricity lines: | --
2. Issues related to OPTCL including shifting of poles and electricity lines: | --
3. Any other issues: | --
Category IV | Issues with respect shifting of Drinking Water Pipelines
1. Issues with PHED | --
2. Issues with RWSS: | --
3. Any other issues: | --
Category V | Issues related to Telecom Infrastructure (IT Department) including BSNL etc.
1. Shifting of BSNL telecom poles and lines: | --
2. Shifting of any other poles and lines: | --
3. Any other issues: | --
Category VI | Issues related Central Government Agencies
1. Issues with NHAI: | --
2. Issues with Railways: | --
3. Any Other Issues: | --
Category VII | Any other issues/Statutory Clearances (Please Specify)
CONSTRUCTION ACTIVITIES
General Details | [6 empty] | Physical Progress of the Project :- * Road Work :- 1. Bituminous Course - (Scope / Completed Length) 2. Base - (Scope / Completed Length) 3. Sub-base - (Scope / Completed Length) 4. Subgrade - (Scope / Completed Length) 5. HP Culvert - (Scope/ Completed in Number) 6. Box-Cell Culvert - (Scope/ Completed in Number) 7. Minor Bridges - (Scope/ Completed in Number) *Bridge Work :- 1. Sub-structure Details - (Scope/ No. of Foundations completed) 2. Super-structure Details - (Scope/ No. of Spans Casted) 3. Approach Road Details - (Scope/ Km completed) *Building Work :- Status of Building work completed till date.
Physical Progress of the Project: | SCOPE OF WORK AS PER CONTRACT |  |  |  | ACHIVEMENT
Agreement drawn on 01.10.2021 |  |  |  |  | C&G = 28 Km Subgrade=4.7Km Embankment=21 Km on progress Majore Bridge on Indra River= Bed for mat machine on progress
Finance Disbursed to Agency: | - |  | Status of Financial Progress (in %): |  | -
Target Date of Completion: | - |  | Status of Physical Progress (in %): |  | -
Design Approval
1. Design Approved | The Design, Plan and Profile for road work approved & Design approved for 1 no Minor Bridge & 1 No Major Bridge.Design to be approved for 1 no Culvert which has to be submitted by the agency.
2. Any issues with the Design | -
-
-
-
-
Procurement Issuess
1. Material Procurement :-
1.1. Issues @ Sand | Issues with Availability : | -
| Issues with Source : | -
| Issues with Transportation : | -
| Issues with Royalty : | -
1.2. Issues @ Stones/Agregates | Issues with Availability : | -
| Issues with Crusher & Quarry : | -
| Issues with Transportation : | -
| Issues with Royalty : | -
1.3. Issues with procuring Special Materials | -
2. Man Power Procurement Issues | -
Issues- with Procurement of Supervising Consultant
3. Machinery Procurement Issues
Quality Issues
Quality Assurance Issues- | -
Scope Of Quality Check-
No. of Tests - |  | No. Of NCR -
Contractual Issues
1. Extesnion of Time (EOT) | -
(a) Is EOT required? | -
(b) If required, has it been applied? | -
(b) If applied, what is the status? | -
2. Deviation | -
(a) Is Deviation required? | -
(b) If required, has it been applied? | -
(b) If applied, what is the status? | -
3. Any other contractual Issues?? | -
-
Any other (Please Specify)
-
Sd/- K.K Panda
| Executive Engineer |  |  | ACE/CCE
| Khariar(R&B) Division |  |  | Balangir (R&B) Circle

## 4.2
PROJECT DETAILS
(Rs. in Crore)
Name of the Project: | Construction of carriage way from 2-Lane to 4-Lane of Ghatiapada-Sinapali road from 52/00 km to 104/650 km (2 Lane 50.650km and 4-Lane 2.00 Km ) Including five major birdges in the district of Nuapada ( Pacakage 4.2) under EPC Contract.
Scheme of the Work | State plan
Project Brief: | Construction of carriage way from 2-Lane to 4-Lane for a length of 52.00 Km | [5 empty] | * Project Brief :- 1. In Road Projects, mention the total length of the project with length of Flexible & Rigid Pavement. No. of Major/ Minor Bridges with span arrangement if any. 2. In Building Projects, mention the Construction Area. 3. In Bridge Projects, mention the Span Arrangement.
Division: | Khariar (R&B) Division | Assembly Consituency: | Khariar | District Name: | Nuapada
Estimated Cost (A/A Cost): (Revised A/A Cost, If any) | 20754.29 Lakhs |  |  | Agreement Value including GST: | 17544.80 Lakhs
Name of the Agency/Contractor with Contact No.: | M/s RKD Construction Pvt. Ltd Mob No.- 7978926534
Date of Commencement | 01.10.2021 | Stipulated Date of Completion: |  | 31.03.2023
Project In charge (Name of EE & Number): | Er. K K Panda (9437136900)
PRE-CONSTRUCTION ACTIVITIES - EXTERNAL | [5 empty] | Updated On (Date):
Category I | Issues with Revenue and Disaster Management Department
1. Land Acquisition Issues: | 26.246 acre (95 tenants): LA under process SIA study & Public hearing to be done from 22.12.2021. NOCs have been received from tenants No issues for construction work
2. Encroachment Issues: | --
3.Issues related to Government Land: | --
4. Any Other issues:
Category II | Issues with Forest and Environment Department
1. Forest Clearance Issues: | --
2. Issues related to Tree Felling permission: | --
3. Wild Life Management Plan | --
4. Any other issues: | --
Category III | Issues with Energy Department
1. Distribution Companies including shifting of poles and electricity lines: | --
2. Issues related to OPTCL including shifting of poles and electricity lines: | --
3. Any other issues: | --
Category IV | Issues with respect shifting of Drinking Water Pipelines
1. Issues with PHED | --
2. Issues with RWSS: | --
3. Any other issues: | --
Category V | Issues related to Telecom Infrastructure (IT Department) including BSNL etc.
1. Shifting of BSNL telecom poles and lines: | --
2. Shifting of any other poles and lines: | --
3. Any other issues: | --
Category VI | Issues related Central Government Agencies
1. Issues with NHAI: | --
2. Issues with Railways: | --
3. Any Other Issues: | --
Category VII | Any other issues/Statutory Clearances (Please Specify)
CONSTRUCTION ACTIVITIES
General Details | [6 empty] | Physical Progress of the Project :- * Road Work :- 1. Bituminous Course - (Scope / Completed Length) 2. Base - (Scope / Completed Length) 3. Sub-base - (Scope / Completed Length) 4. Subgrade - (Scope / Completed Length) 5. HP Culvert - (Scope/ Completed in Number) 6. Box-Cell Culvert - (Scope/ Completed in Number) 7. Minor Bridges - (Scope/ Completed in Number) *Bridge Work :- 1. Sub-structure Details - (Scope/ No. of Foundations completed) 2. Super-structure Details - (Scope/ No. of Spans Casted) 3. Approach Road Details - (Scope/ Km completed) *Building Work :- Status of Building work completed till date.
Physical Progress of the Project: | SCOPE OF WORK AS PER CONTRACT |  |  |  | ACHIVEMENT
Survey-PCL marking=52.65Km TBM traversing=52.65Km OGL recording=18.00Km Highway-clearing & grubbing=18.00 Km Embankment=12.00Km Subgrade=7.00Km Structure Return wall-4 nos. Box culvert(I/P)=02 Nos. Minor Bridge(I/P)=03 Nos. RE panel casting=50Nos.
Finance Disbursed to Agency: | - |  | Status of Financial Progress (in %): |  | -
Target Date of Completion: | - |  | Status of Physical Progress (in %): |  | -
Design Approval
1. Design Approved | The Design, Plan and Profile for road work approved . Design approved for 4 nos minor bridges& 6 nos of culverts. For 4 nos of major bridges on river Udanti. The agency has submitted the necessary compliance of observation(as per Addl. C.E (Bridges), Directorate of design's observations ) on design and drawing vide Lr No.RKD/Ghatipaqda-Sinapali 4.2/2021-22/079 & 080 Dt.17.12.2021, which is under scruitiny in the office of the Directorate of design . 1 no of minor & 1 no of major bridge is yet to be submitted by the agency
2. Any issues with the Design | -
-
-
-
-
Procurement Issuess
1. Material Procurement :-
1.1. Issues @ Sand | Issues with Availability : | -
| Issues with Source : | -
| Issues with Transportation : | -
| Issues with Royalty : | -
1.2. Issues @ Stones/Agregates | Issues with Availability : | -
| Issues with Crusher & Quarry : | -
| Issues with Transportation : | -
| Issues with Royalty : | -
1.3. Issues with procuring Special Materials
2. Man Power Procurement Issues | -
Issues- with Procurement of Supervising Consultant
3. Machinery Procurement Issues
Quality Issues
Quality Assurance Issues-
Scope Of Quality Check-
No. of Tests - |  | No. Of NCR -
Contractual Issues
1. Extesnion of Time (EOT) | -
(a) Is EOT required? | -
(b) If required, has it been applied? | -
(b) If applied, what is the status? | -
2. Deviation | -
(a) Is Deviation required? | -
(b) If required, has it been applied? | -
(b) If applied, what is the status? | -
3. Any other contractual Issues?? | -
-
Any other (Please Specify)
Sd/- K.K Panda
| Executive Engineer |  |  | ACE/CCE
| Khariar(R&B) Division |  |  | Balangir (R&B) Circle